## SepTargets
SNo | Target
1 | FD Fan foundation casting completion
2 | 1000MT erection in Unit 3 ACC
3 | All HT switchgear charging of Unit 3
4 | Start of BAIM silo erection in Unit 3
5 | ST 2 and UAT3 charging
6 | 60 P91/92 joints in Unit 3. Sep achievement was - 28

## Tonnage
Unit | Component | Tonnage Completed | Total Tonnage | Percentage
Unit 1 | Boiler-1 | 58679 | 59584 | 98.48%
Unit 1 | ESP- 1 & Absorber | 20312 | 20879 | 97.28%
Unit 1 | Critical Piping U1 | 5159 | 5159 | 100%
Unit 1 | ACC1 | 10800 | 10800 | 100%
Unit 1 | MPH-1 | 10535 | 10535 | 100%
Unit 2 | Boiler-2 | 58503 | 60168 | 97.23%
Unit 2 | ESP-2 | 18741 | 18087 | 103.6%
Unit 2 | Critical Piping U2 | 5800 | 5903 | 98.26%
Unit 2 | ACC2 | 10690 | 10820 | 98.8%
Unit 2 | MPH-2 | 13293 | 13400 | 99.2%
Unit 3 | Boiler-3 | 40824 | 66363 | 61.52%
Unit 3 | Piping-3 | 1644 | 5309 | 30.97%
Unit 3 | ESP-3 incl control room | 11284 | 14724 | 76.64%
Unit 3 | ACC3 | 4615 | 10800 | 42.73%
Unit 3 | MPH-3 | 7599 | 7600 | 99.99%

## AugustTargets
SNo | Target
1 | Boiler DHT - 10.08.26- Completed on 17.08.26
2 | 1000MT erection in Unit 3 ACC
3 | 1st HT Switchgear charging in Unit 3 - 14.08.26
4 | Completion of FD 3A/ PA 3A foundation - 30.08.26
5 | Start of Bottom ash hopper erection work - 17.08.26
6 | 60 P91/92 joints in Unit 3. July achievement was - 28