## Tasks
Date | Activity | Status | Responsibility
2026-08-25 | Hotbox - all 4 walls erection completion | Completed | ME
2026-08-03 | UNIT#3 hot box Side plate erection by 03.08.26 | Completed | ME
2026-08-10 | ISH Foundation handover | Completed | CCD
2026-08-17 | Boiler DHT - Target completion | Completed | ME
2026-09-15 | 1st HT Switchgear charging | Completed | EED
2026-09-04 | 2nd TDBP Deck Casting | Completed | CCD
2026-08-17 | MPH Columns casting completion and scaffolding removal | Completed | CCD
2026-11-15 | Transfer Tower Foundation handover | Delayed R0 - 15-09-26/15-10-26 | CCD
2026-10-30 | Tripper floor - 50% structure works completion | Delayed R0 - 25.08.26/15.09.26/30.09.26 | ME
2026-09-25 | ESP-CR 8.5m structure works completion | Completed | ME
2026-10-10 | AHP Stg-2 Foundation handover | Completed | CCD
2026-11-30 | TG Box up - Target completion | Delayed R0 - 31-08-26 | ME
2026-10-17 | ESP-CR 8.5Mm slab casting | Delayed -30.09.26 | CCD
2026-09-15 | ST-2 charging | Completed | ME
2026-12-10 | TG Oil Flushing completion | Delayed R0 - 31.10.26,18.11.26 | C&T
2026-12-25 | Boiler Light up | Delayed - 15.11.26 | C&T
2027-01-15 | Steam Blowing Completion | Delayed - 15.12.26 | C&T
2027-02-26 | Sync | Delayed - 07.02.27 | C&T
2027-03-10 | Full Load | Delayed - 25.02.27 | C&T
2027-03-15 | Trial Operation |  | C&T
2026-08-20 | Hotbox bottom plate erection | Completed | ME
2026-12-15 | Chimney 5th segment erection | Delayed - 30.11.26 | CCD
2026-11-10 | Chimney 4th segment erection | Delayed - 26.10.26 | CCD
2026-10-07 | Chimney 3rd segment erection | Completed | CCD
2027-01-15 | Transition duct erection completion |  | ME
2026-10-25 | CER to ESP RHS Foundation completion | Delayed -30.06.26/15.07.26/30.07.26/10.08.26/31.08.26/10.10.26 | CCD
2026-10-25 | CER to ESP LHS Foundation completion | Delayed -30.06.26/15.07.26/30.07.26/14.08.26/05.09.26 | CCD
2026-09-05 | CER to Boiler Foundation completion | Completed | CCD
2026-10-31 | ESP to ESP Control Room (LHS) – Electromech/RVPR | Delayed -30.07.26/20.08.26/10.09.26/15.10.26 | CCD
2026-09-10 | ESP to ESP Control Room (RHS) | Completed | CCD
2026-10-31 | FD 3A foundation completion | Delayed - 30.08.26/30.09.26/15.10.26 | CCD
2026-10-06 | PA 3A foundation completion | Completed | CCD
2026-09-30 | BA INT Silo foundation completion | Completed | CCD
2026-09-25 | AHP MCC3 panel erection front | Delayed - R0 - 15.09.26 | CCD
2026-08-20 | Surge hopper foundation completion | Completed | CCD
2026-09-07 | BA Hopper foundation completion | Completed | CCD
2026-09-20 | ESP-CR 0M floor finishing works works completion by | Completed | CCD
2026-10-05 | ACC - Street 2 ATT | Completed | ME
2026-10-15 | ACC - Street 1 ATT | Delayed - 20.09.26 | ME
2026-10-25 | ACC - Street 3 ATT | Delayed - 30.09.26 | ME
2026-11-05 | ACC - Street 4 ATT | Delayed - 25.10.26 | ME
2026-11-15 | ACC - Street 5 ATT | Delayed - 05.11.26 | ME
2026-12-05 | ACC - Street 6 ATT |  | ME
2026-12-29 | ACC - Street 7 ATT |  | ME
2027-01-14 | ACC - Street 8 ATT |  | ME
2026-12-26 | ACC - Common Duct ATT |  | ME
2026-12-15 | MDBP Trial in RC |  | ME
2026-10-25 | MDBP motor trial | Delayed -17.10.26 | EED
2026-08-31 | Street 1 ACC erection completion | Completed | ME
2026-09-25 | Street 2 ACC erection completion | Completed | ME
2026-10-15 | Street 3 ACC erection completion | Delayed - 10.09.26/20.09.26/30.09.26 | ME
2026-10-31 | Street 4 ACC erection completion |  | ME
2026-10-31 | Street 5 ACC erection completion |  | ME
2026-11-20 | Street 6 ACC erection completion |  | ME
2026-12-10 | Street 7 ACC erection completion |  | ME
2026-12-29 | Street 8 ACC erection completion |  | ME
2026-09-20 | Street 1 Riser erection | Completed | ME
2026-10-25 | Street 4 Riser erection | Delayed - 14-09-26/10-10-26 | ME
2026-10-31 | Street 5 Riser erection | Delayed - 30-09-26/10-10-26 | ME
2026-10-20 | Street 6 Riser erection |  | ME
2026-10-31 | Street 7 Riser erection |  | ME
2026-09-12 | 7AB gallery erection | Completed | CCD
2026-10-13 | BMCC to CER Cantilever cable gallery-start | Completed | CCD
2026-09-10 | C row balance cable gallery handover | Completed | CCD
2026-08-31 | Handover of cable gallery upto AHP MCC3 | Completed | CCD
2026-10-25 | 0BE Board charging | Delayed - 23.09.26/30.09.26 | EED
2026-11-05 | 3.3KV - 3CA Board charging | Delayed - 26.09.26/10.10.26/20.10.26 | EED
2026-10-30 | 3BA Board charging | Delayed - 29.09.26/05.10.26 | EED
2026-10-13 | 3BB Board charging | Delayed - 16.09.26/30.09.26 | EED
2026-10-10 | ST-2 charging | Completed | EED
2026-11-04 | UAT-3A charging | Delayed - 15.09.26/30.09.26/15.10.26 | EED
2026-10-15 | Start of TG Lube oil flushing | Delayed - 05.10.26 | ME
2026-12-15 | MS Line Hydro Test | Delayed -15.11.26 | ME
2026-12-20 | HRH Line Hydro Test | Delayed -30.11.26 | ME
2026-12-20 | CRH Line Hydro Test | Delayed -25.11.26 | ME
2026-11-15 | BFD/BFR/BFS Hydro Test | Delayed -31.10.26 | ME
2026-10-25 | Eco Hopper erection | Delayed - 30.09.26/10.10.26/15.10.26 | ME
2026-10-22 | Condenser pit staircase completion |  | CCD
2026-10-07 | Hotbox -0M TG side platform completion | Completed | CCD
2026-09-30 | Hotbox -0m Gen side platform completion | Completed | CCD
2026-10-20 | C row - TDBP area platform completion |  | CCD
2026-10-07 | TDBP Deck staircase completion |  | CCD
2026-10-15 | MPH A row sheeting works completion |  | CCD
2026-10-25 | MPH C row sheeting works completion |  | CCD
2026-10-28 | Boiler TG Interconnection beam works from civil side | Completed | CCD
2026-10-05 | Electrical - 250 manpower by Shriram |  | EED
2026-10-10 | MOT, TG ECW- Cable tray completion |  | EED
2026-09-30 | FD/PA 3A cable tray completion |  | EED
2026-10-10 | Boiler LHS Cable tray riser completion |  | EED
2026-10-25 | Boiler RHS Cable tray riser completion |  | EED
2026-10-06 | Mot AOP, Centrifuge and MDBP LOP trial | Completed | EED
2026-10-25 | 0DC Board charging | Delayed - 15.10.26 | EED
2026-10-30 | 3DB-TMCC Charging | Delayed - 25.10.26 | EED
2026-11-05 | 3DG - DG MCC Charging | Delayed - 25.10.26 | EED
2026-10-05 | Mill unloading bay area paving completion | Completed | CCD
2026-10-20 | K row drain and approach completion | Delayed - 10.10.26 | CCD
2026-10-19 | Cable rack foundation/Pull pit/Duct bank for FD/PA 3B | Delayed - 10.10.26 | CCD
2026-10-20 | Boiler area paving - RHS from PA Fan to APH completion |  | CCD
2026-10-15 | Boiler Unit 1 Passenger lift handover | Completed | ME
2026-10-10 | ESP Unit 1 Hoists commissioning |  | ME
2026-09-30 | Unit 1 ESP-CR lift commissioning |  | ME
2026-10-31 | Unit 2 Boiler all hoists commissioning completion |  | ME
2026-10-05 | Unit 2 Boiler MC room lift casting | Completed | CCD
2026-10-05 | PA Fan 3A casting completion | Completed | CCD
2026-11-30 | ID Fan motor trial |  | EED
2026-12-14 | TG Barring |  | EED
2026-10-28 | Deaerator - HT | Delayed - 20.10.26 | ME
2026-10-15 | SG ECW lines readiness for HT |  | ME
2026-10-30 | TG ECW Lines readiness for HT | Delayed - 25.10.26 | ME
2026-10-14 | MOT VEF - A load trial | Completed | EED
2026-10-16 | MOT Room & Oil Canal mulsifier system readiness (Sprinkler flushing) |  | ME
2026-10-26 | Seal Oil Skid mulsifier system readiness |  | ME
2026-10-18 | DCS Readiness from Siemens for Lube oil flushing |  | C&I
2026-10-16 | MOT & SOST Internal cleaning & inspection |  | Commissioning
2026-10-17 | Permanent lighting in Oil canal |  | EED
2026-10-17 | MOT Cleaning and Oil Filling |  | Commissioning
2026-10-17 | Starting Oil flushing (Supply & Return oil lines flushing) |  | Commissioning
2026-10-15 | Seal oil System Piping readiness for cardboard bursting |  | Commissioning
2026-10-19 | Seal oil System Piping complete readiness (for flushing) |  | ME
2026-10-15 | MDBFP Lube oil flushing | Completed | Commissioning
2026-10-25 | ECW Overhead Tank & Piping readiness |  | ME
2026-10-28 | ECW Overhead Tank Normal Makeup and Emergency Makeup Readiness |  | ME
2026-11-06 | TG and SG ECW Pumps Motor no load Trial |  | EED
2026-11-11 | TG ECW Pump-A/B/C load Trial |  | ME
2026-10-30 | ACW Piping completion and load trial |  | ME
2026-10-17 | TDBP EOT Commissioning |  | ME
2026-10-18 | TDBP 2B DRIVE Turbine placement |  | ME
2026-10-17 | LPT Outer casing top half placement, and checking |  | ME
2026-10-23 | LPT inner casing bottom half placement–Start from 23-10-26 |  | ME
2026-10-26 | LPT Rotor placement |  | ME
2026-11-10 | LPT boxup |  | ME
2026-10-23 | 150 manpower by alternate agency M/s M&S in Piping scope |  | ME
2026-11-07 | Toggle duct erection |  | ME
2026-11-10 | APH 3A erection start |  | ME
2026-10-23 | APH 3B Lube oil flushing start |  | ME
2026-10-25 | FD 3B motor trial |  | EED
2026-10-22 | Cable rack gallery erection completion upto FD 3A by |  | CCD
2026-10-18 | CR-11,12 cable rack foundation completion by (only bolt lift pending) |  | CCD
2026-10-22 | Approach to Boiler RHS from CR-11, 12 by |  | CCD
2026-10-20 | K row drain completion by |  | CCD
2026-10-25 | ESP 3 F pass inlet area paving completion by (Last commitment - 19-09-26) |  | CCD
2026-10-20 | Material removal near ESP-CR/ Chimney area for approach to ESP CR LHS transformer civil works by |  | CCD
2026-11-10 | ESP-CR LHS 4 nos transformer foundation civil works completion by |  | CCD
2026-10-31 | 11m ESP-CR structure and deck sheeting completion by |  | ME
2026-11-15 | ACC - GT and IPBD foundation clearance |  | ME
2026-11-30 | ACC - Clearance for cable rack structure